## Sheet1
Risk Assesment
Risk | Description | Likelihood Scale: 1-5 (5 = high risk) | Severity Scale: 1-5 (5 = high risk) | Product of Likelihood and Severity | Risk Mitigation | Responsible
Risk 1 | Lack of time before hand-in/assignment | 2 | 3 | 6 | Assign internal deadlines for specific tasks, more classwork. | Everyone
Risk 2 | Late hand-in/assignment | 2 | 3 | 6 | Assign internal deadline for specific tasks. | Everyone
Risk 3 | Plagiarism | 1 | 5 | 5 | Reference all third party information/sources. | Person who plagarised work
Risk 4 | Unequal workload | 2 | 3 | 6 | Divide tasks evenly between team members. | Everyone
Risk 5 | Crunch time | 2 | 3 | 6 | Complete most important tasks early on and leave less significant work for the end. | Everyone